## Time Estimation
ID | Time | Title | May 1W | [6 empty] | May 2W | [6 empty] | May 3W
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
1 | 08:00 ~ 17:00 | Lecture
2 | 17:00 ~ 18:30 | Dinner
3 | 18:30 ~20:30 | Team Project /Pre-Course assignment
4 | 20:30 ~ | Free Study
Total Available Time = Team member x Team Project Time = 6 x 96 |  |  | May 1W 6: 576 (hours)
ID | Time | Title | May 1W 1: May 4W; May 2W 8: June 1W; May 3W 15: June 2W | June 3W | [6 empty] | June 4W
|  |  | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
| 08:30 ~ 12:00 | Lecture
| 13:00 ~ 14:00 | Lunch
| 14:00 ~18:00 | Team Project |  | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4
| 18:00 ~ | Free Study

## WBS
ID | Task category | Function Level |  | Estimation | May 1W | [5 empty] | May 2W | [6 empty] | May 3W | [6 empty] | May 4W | [6 empty] | June 1W | [6 empty] | June 2W | [6 empty] | June 3W | [6 empty] | June 4W
|  | Level1 | Level2 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
1 | Planning | Team setup |  |  | May 1W 3: 10
2 |  | Scheduling |  |  | May 1W 3: 5
3 |  | Role decision |  |  | May 3W 19: 5
4 |  | Milestone |  |  | May 3W 19: 5
5 |  | discussiong development process |  |  | May 3W 19: 5
6 |  | Collaboration setup (google doc)
7 |  | Source management
8 |  | arduino environment setup
9 | Requirements | Document Review |  |  | May 1W 6: 5
10 |  | Use Case |  |  | May 2W 9: 10
11 |  | Use Case Scenario |  |  | May 2W 9: 5
12 |  | Functional Requirement |  |  | May 1W 6: 5
13 |  | Quality Attribute |  |  | May 2W 10: 10
14 |  | Quality Attribute Scenario |  |  | May 2W 10: 5
15 |  | Constraint |  |  | May 3W 16: 10
16 |  | Domain Model |  |  | May 3W 16: 5
17 | Design | Context Diagram
18 |  | Architectrue design | static view
19 |  |  | dynamic view
20 |  |  | physical view
21 |  | stream design
22 | Implementation | Controller | lift gate
23 |  |  | lane detection
24 |  |  | space detection
25 |  |  | blink LED
26 |  |  | entry detection
27 |  | Driver app | log-in
28 |  |  | reservation
29 |  |  | confirmation info
30 |  |  | https (communication protocol)
31 |  |  | 인증서버 고려
32 |  | Attendant app | log-in
33 |  |  | status
34 |  |  | push alarm
35 |  |  | https
36 |  |  | PSI -> driver
37 |  |  | door open ??
38 |  | Owner app | statistic
39 |  |  | add new analysis function
40
41 |  | Server | 아비터
42 |  |  | 인증
43 |  |  | 분산
44 |  |  | MQTT
45 |  |  | 예약&주차확인 로직
46 |  |  | DB관리
47 |  |  | 주차장 상태 monitor
48 |  |  | 통계
49 |  |  | control controller
50 |  |  | push to attendant
51 |  |  | payment
52 | Testing | Unit test
53 |  | Integration test
●
●
●
●
●
●
●
●
●
●
●
●

## WBS_example
ID | Task category | Function Level |  | Estimation | May 1W | [5 empty] | May 2W | [6 empty] | May 3W | [6 empty] | May 4W | [6 empty] | June 1W | [6 empty] | June 2W | [6 empty] | June 3W | [6 empty] | June 4W
|  | Level1 | Level2 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
1 | Planning | Team setup |  | 8
2 |  | Scheduling |  | 12
3 |  | Role decision |  | 2
4 |  | Milestone |  | 4
5 |  | discussiong development process |  | 8
6 |  | Collaboration setup (google doc) |  | 2
7 |  | Source management |  | 8
8 |  | arduino environment setup |  | 12
9 | Requirements | Document Review |  | 8
10 |  | Use Case |  | 4
11 |  | Use Case Scenario |  | 4
12 |  | Functional Requirement |  | 16
13 |  | Quality Attribute |  | 24
14 |  | Quality Attribute Scenario |  | 12
15 |  | Constraint |  | 8
16 |  | Domain Model |  | 4
17 | Design | Context Diagram |  | 4
18 |  | Architectrue design | static view | 12
19 |  |  | dynamic view | 10
20 |  |  | physical view | 6
21 |  | stream design |  | 6
22 | Implementation | Controller | lift gate | 12
23 |  |  | lane detection | 8
24 |  |  | space detection | 8
25 |  |  | blink LED | 12
26 |  |  | entry detection | 8
27 |  | Driver app | log-in | 12
28 |  |  | reservation | 8
29 |  |  | confirmation info | 6
30 |  |  | https (communication protocol) | 12
31 |  |  | 인증서버 고려 | 12
32 |  | Attendant app | log-in | 12
33 |  |  | status | 12
34 |  |  | push alarm | 12
35 |  |  | https | 12
36 |  |  | PSI -> driver | 12
37 |  |  | door open ?? | 12
38 |  | Owner app | statistic | 12
39 |  |  | add new analysis function | 12
40 |  |  |  | 12
41 |  | Server | 아비터 | 12
42 |  |  | 인증 | 12
43 |  |  | 분산 | 12
44 |  |  | MQTT | 16
45 |  |  | 예약&주차확인 로직 | 16
46 |  |  | DB관리 | 16
47 |  |  | 주차장 상태 monitor | 16
48 |  |  | 통계 | 16
49 |  |  | control controller | 16
50 |  |  | push to attendant | 16
51 |  |  | payment | 16
52 | Testing | Unit test |  | 16
53 |  | Integration test |  | 16
Total hours |  |  |  | 576

## Sprint1_example
| Sprint Period | 5/22 ~ 5/28
| Story | Make ADS Document as Finale Presentation Quality
| Delivery | ADS Document
| Test Plan | Mentor Review
ID | Baglogs |  | Estimation | To-Do | In Progress |  | Done
| Level1 | Level2 |  | Scheduling | Logs | Assingnee | Logs | Spent time
1 | Team setup |  | 8 | Milestone
2 | Scheduling |  | 12 | discussiong development process
3 | Role decision |  | 2 | Collaboration setup (google doc)
4 | Milestone |  | 4 | Source management
5 | discussiong development process |  | 8 | arduino environment setup
6 | Collaboration setup (google doc) |  | 2 | Document Review
7 | Source management |  | 8 | Use Case
8 | arduino environment setup |  | 12 | Use Case Scenario
9 | Document Review |  | 8 | Functional Requirement
10 | Use Case |  | 4 | Quality Attribute
11 | Use Case Scenario |  | 4 | Quality Attribute Scenario
12 | Functional Requirement |  | 16 | Constraint
13 | Quality Attribute |  | 24 | Domain Model
14 | Quality Attribute Scenario |  | 12 | Context Diagram
15 | Constraint |  | 8
16 | Domain Model |  | 4
17 | Context Diagram |  | 4
18 | Architectrue design | static view | 12
19 |  | dynamic view | 10
20 |  | physical view | 6
21 | stream design |  | 6
22 | Controller | lift gate | 12
23 |  | lane detection | 8
24 |  | space detection | 8
25 |  | blink LED | 12
26 |  | entry detection | 8
27 | Driver app | log-in | 12
28 |  | reservation | 8
29 |  | confirmation info | 6
30 |  | https (communication protocol) | 12
31 |  | 인증서버 고려 | 12
32 | Attendant app | log-in | 12
33 |  | status | 12
34 |  | push alarm | 12
35 |  | https | 12
36 |  | PSI -> driver | 12
37 |  | door open ?? | 12
38 | Owner app | statistic | 12
39 |  | add new analysis function | 12
40 |  |  | 12
41 | Server | 아비터 | 12
42 |  | 인증 | 12
43 |  | 분산 | 12
44 |  | MQTT | 16
45 |  | 예약&주차확인 로직 | 16
46 |  | DB관리 | 16
47 |  | 주차장 상태 monitor | 16
48 |  | 통계 | 16
49 |  | control controller | 16
50 |  | push to attendant | 16
51 |  | payment | 16
52 | Unit test |  | 16
53 | Integration test |  | 16
Total hours |  |  | 576