## Slide 1
Final Presentation
Team #2 - NOT YET
2016.06.24

## Slide 2
1. Overview of programmatic aspects
  About Team #2 – NOT YET
  Schedule
  Time Logs
  Configuration Management
2. Overview of the architectural design
  Context Diagram and Influential Architecture Drivers
  Design decisions and alternatives
  Architecture in static, dynamic, physical perspective
3. Test
  Test case
  Verification, Validation
4. Lessons learned & Q/A
  Lessons learned
  Q/A
  Table of contents

## Slide 3
  Team members – NOT YET

## Slide 4
Daniel Plakosh | Sunghoon Yun | Sangjun Lee | Gladvin Chinnadurai | Byounghoon Kim | Wonhong Kwon | Gunwoo Kim | Hidden Memeber
  Team members – NOT YET

## Slide 5
  Organization and roles
 | Team Mentor
 | Daniel Plakosh
 | Team Leader
 | Sunghoon Yun
 | Chief Architect
 | Wonhong Kwon
 | Lead Engineer. (Server)
 | Gunwoo Kim
 | Lead Engineer (Protocol)
 | Byounghoon Kim
 | Lead Engineer (Facility)
 | Sangjun Lee
 | Lead Engineer. (Owner)
 | Gladvin Chinnadurai
Title | Role Assignment | Deliveries | Common Job
Team Leader | Project Management | WBS, Schedule , Agile Sprint | Planning. Architectural Discussion. Test.
Chief Architect | Architectural Design | ADS, Architecture documents. | 
Lead Engineer(Protocol) | Communication design. Driver Application | Comm library. Driver App source. | 
Lead Engineer(Facility) | Facility control and user interface | Facility and kiosk source. | 
Lead Engineer(Server) | Server logic and redundancy. Pub/Sub Pattern implementation. | Server and arbiter source. | 
Lead Engineer(Owner) | Owner business logic design - statistics | Owner and statistics source. | 

## Slide 6
Jun 1W
Jun 2W
Sprint 2
Jun 3W
Sprint 4
Jun 4W
Sprint 3
Plan
Analysis
Experiment
Design
Implementation
Testing
Documentation
Sprint 1
Sprint 1, 2 Plan
Mentor meeting
Use case
Context diagram
QA refine
MQTT Server/Client
Arduino control
Research architectural Pattern
PC environment setup
Git Hub setup
Start Time log, ADS
Sprint 3 Plan
Mentor meeting
Risk Mitigation meeting
FR refine
QA refine
Arduino USB communication
Server DB
Start View , MQTT Topic,
DB Schema Design
Server (communication,
redundancy, DB)
Sprint2 result test
Planning v1.0
Sprint and Time logs v1.0
Failure model list v1.0
Sprint 4 Plan
Mentor meeting
MQTT Security
Research architectural Pattern
Research Tatic
Start detail design
Server logic
Driver, Owner, Attendant,
Facility, Kiosk Application
System test (16 test case)
System test case v1.0
Mentor meeting
Use case
Context diagram
QA refine
MQTT Server/Client
Arduino control
Research architectural Pattern
Server logic
Driver, Owner, Attendant,
Facility, Kiosk Application
System test (31 test case)
System test case v1.1
Final Presentation v1.0
  Schedule
We used agile style development process.
We made 4 sprint . Each sprint has own iteration of working categories.

## Slide 7
  Schedule
Estimated backlogs are used to make a refined WBS Plan.
New WBS is made using Gant Chart.
We had tracking project by the chart.
This is full version of WBS.
You need chrom plug-in (gantter tool)

## Slide 8
We had estimated the total time as 576 hours using a simple equation.
6 (people) x 24 (working day) x 4 (working time/day) .
We had made a initial version of WBS that have 53 items for the project and split work load as table
Category | Hours | Load (%)
Plan | 56 | 10
Analysis | 120 | 20
Design | 150 | 26
Implementation | 130 | 24
Testing | 120 | 20
Total | 576 | 100
  Time logs - 1
Chart: Intial Estimation
| Plan | Analysis | Design | Implementation | Test
 | 56 | 120 | 150 | 130 | 120

## Slide 9
  Time logs - 2
In actual project, we used agile style development process and added two more categories.
We made backlogs every week for next sprint and estimated working time with the logs.
The result is as below.
Chart: Actual Used
| Plan | Analysis | Design | Experiment | Implementation | Test | documentation
 | 59.6 | 38.5 | 48 | 127.3 | 215 | 19 | 113.2
Chart: Sprint Estimation
| Plan | Analysis | Design | Experiment | Implementation | Test | documentation
 | 31 | 44 | 50 | 112 | 228 | 8 | 94
 | sprint1 | sprint2 | sprint3 | sprint4 | total
Plan | 9 | 8 | 8 | 6 | 31
Analysis | 38 | 6 | 0 | 0 | 44
Experiment | 36 | 14 | 0 | 0 | 50
Design | 40 | 59 | 4 | 9 | 112
Implementation | 4 | 10 | 162 | 52 | 228
Test |  | 2 | 2 | 4 | 8
documentation | 14 | 24 | 16 | 40 | 94
Total |  |  |  |  | 567
 | sprint1 | sprint2 | sprint3 | sprint4 | total
Plan | 28.6 | 7 | 18 | 6 | 59.6
Analysis | 35.5 | 3 | 0 | 0 | 38.5
Experiment | 31 | 7 | 10 | 0 | 48
Design | 34.8 | 54.5 | 30 | 8 | 127.3
Implementation | 3 | 42 | 109 | 61 | 215
Test |  | 6 | 4 | 9 | 19
documentation | 6.2 | 19 | 31 | 57 | 113.2
Total |  |  |  |  | 620.6

## Slide 10
Chart: 
| Plan | Analysis | Experiment | Design | Implementation | Test | documentation
Initial estimation | 56 | 120 | 0 | 150 | 130 | 120 | 0
sprint estimation | 31 | 44 | 50 | 112 | 228 | 8 | 94
Actual time | 59.6 | 38.5 | 48 | 127.3 | 215 | 19 | 113.2
  Time logs - 3
Plan and Design work load estimation is similar between initial and actual used but others are very different.
Sprint estimation and actual used time graphs are almost matched.

## Slide 11
  Configuration Management
Managed Artifacts & Tools
  Documents (Google Drive & GitHub.com)
  Database Schema (GitHub.com)
  Source Code & Issues (GitHub.com)
Artifacts baselining & pre-condition
  Documents (After review meeting)
  Database Schema (After peer review. Schema and sample data)
  Source Code (After sub feature is in working condition)
  Information Propagation
  Hangout Group
  Sync up meetings (After lunch and before leaving to rooms)

## Slide 12
Driver
Attendant
Owner
Product Developer
System Operator
Credit Card Payment System
Sure-Park System
Driver’s Information
A
B
Data flow from A to B
Add algorithm
A
B
A interact with B
Status
Statistics
Parking Facility
Sensor Data
Control
Configure
Credit Card Information
System
External Entity
System Boundary
A
B
Control flow from A to B
  System Context Diagram

## Slide 13
  Influential architecture drivers

## Slide 14
Process
A
B
Data flow from A to B
Facility
Controller
Sure-Park
Service System
  Architecture Design – 1st Decomposition (dynamic perspective)

## Slide 15
Process
A
B
Data flow from A to B
Pub/Sub
Event Bus
Publisher
Subscriber
Publisher
Subscriber
Local Server
Local Server
Client
Client
Main Server
Client
Client
Client
Client
  Architecture Design – Patterns for high-level architecture (dynamic perspective)

## Slide 16
Pub/Sub
Event Bus
Facility Controller
Sure-Park
Reservation
System
Facility
Manager
Sure-Park
Statistics
Viewer
Sure-Park
Manager
Sure-Park
Processing
System
Facility
User I/F
Process
Data Repository
A
B
Data flow from A to B
  Architecture Design – 2nd Decomposition (dynamic perspective)

## Slide 17
Pub/Sub
Event Bus
Facility Controller
Sure-Park
Processing
System
Process
A
B
Data flow from A to B
PING
PING
ECHO
ECHO
  Architecture Design – Tactic #1: Ping/Echo (dynamic perspective)

## Slide 18
Pub/Sub
Event Bus
Sure-Park
Processing
System
Process
Wireless Network Connection
Sure-Park
Processing
System
Process running on the server
Data Repository
  Architecture Design – Tactic #2: Passive Redundancy (dynamic perspective)

## Slide 19
Ping/Echo
Modifiability
(Add to system)
Security
(Ping flood)
Performance overhead
Detect service denial
Tactic
Tradeoffs
Cost
Modifiability
(Add to system)
  Architecture Design – Relief the negative effects of ping/echo tactic

## Slide 20
MQTT Broker (Mosquitto)
Facility Controller
Thread
Facility
User I/F
A
B
Message flow
A
B
Register to listen for event
Java method call
Facility
Manager
Sure-Park
Manager
Sure-Park
Statistics
Viewer
Sure-Park Reservation
System
Sure-Park
Processing
System
Communication Manager (Thread)
Process
Database
A
B
Data flow
External Entity
Callback
CCPS
  Architecture Design – Dynamic Perspective

## Slide 21
Object
Thread
Data Flow
Client Channel
Server Channel
Publish Channel
Subscribe Channel
Component
MQTT
Broker
Process
  Architecture Design – Communication Manager (dynamic perspective)

## Slide 22
Module
Database
3rd Party
Paho
(MQTT Lib.)
Credit Card Proxy
Communication Manager
DB Manager
Vert.x Framework
Facility Status
Reservation
Security and Account
Statistics
User Interface
A
B
A uses B
Layer
UI Layer
Business Logic Layer
Abstraction Layer
Framework Abstraction
Framework
Layer
Facility Control
Arduino Framework
pubsub
client
Arduino Communication Wrapper
  Architecture Design – Static Perspective

## Slide 23
Facility
Controller
Sure-Park
Statistics
Viewer
Sure-Park
Manager
Facility
Manager
Sure-Park
Reservation
System
Sure-Park
Processing
System
Facility
User I/F
Paho MQTT Library
Vert.x Framework
Arduino Framework
Communication Manager
Arduino Communication Wrapper
Business Logic Layer
pubsub
client
DB Manager
Credit Card Proxy
Module
Database
3rd Party
A
B
A uses B
Layer
Abstraction Layer
Framework Layer
  Architecture Design – Static Perspective

## Slide 24
Arduino (Main)
Facility
Controller
Kiosk
Facility
User I/F
MQTT Broker
A
SW ‘A’ running on a user machine
A
SW ‘A’ running on a server machine
B
A
SW ‘A’ running on a machine ‘B’
802.11 Wi-Fi
Sure-Park Processing System
Wi-Fi Router
Network Equipment
Sure-Park Processing System
Facility Manager
Sure-Park Reservation System
Sure-Park Statistics Viewer
Sure-Park
Manager
A
DB on a server
Cloud Environment
Ethernet Router
Firewall
Ethernet
Public Internet
USB Connection
Private Network
Firewall
Arduino (Sub)
Facility
Controller
1
0..*
Parking Facility
1
  Architecture Design – Physical Perspective

## Slide 25
  We had experiments before implementation
  We had test the system end of every sprint.
  Test , Verification, and Validation

## Slide 26
WBS |  | Description | Number |  | precondition | Testing Sequence | Expected Results
L1 | L2 |  |  |  |  |  | 
Server | Server (switching function - Redundancy) | If primary server is unavailibe because of power down or network trouble, secondary server should work within guaratted time. | T-1 |  |  | 1. Tester operates sure-park system generally. 2. Tester shut down power or pull off network cable of the primary server | The system runs normal status within guaranteed time.
Driver Application | Driver Application (sign up) | Driver should sign up the sure-park system for using reservation application | T-5 |  |  | 1. Driver input a email addree, password, card number 2. Server authorized the information. | Sign up is done.
 | Driver Application (log in/out) | Driver should log in the sure-park system for reserving a parking lot. | T-6 |  | Driver app is executed. | 1. Tester inserts correct email and password | Driver app is connected server and shows own UI.
Attendant Application | Attendant Application(Popup message) | If unexpected situation occurs in syste like facility power down, Attendant can know the situation by alarm of application. | T-16 | Attendant logged in the app. |  | 1. Test turns off the facility power. 2. Server sends a message to Attendantapp. | Attendant app shows a alarm (Facility down).
  We made test cases
  Test Cases

## Slide 27
  We used github issue for issue tracking
  Issue tracking system

## Slide 28
Organization perspective
  Didn’t assign each one’s responsibility concretely  too much discussion, but no decisions made
Technology perspective
  Obsessed with technologies prior to decision-making about the architecture
Architecture perspective
  Too focused on dynamic perspective
  Hard to have consistent views across static, dynamic, and physical perspectives
Are we architects now ?
not yet, Not Yet, and NOT YET
  Lessons learned

## Slide 29
Any questions ?
I just want to go home…
Please don’t ask me anything