## Sprint1
| Sprint Period | 5/22 ~ 6/4
| Story | Make Design Document and prepare Implementation |  |  |  | Question
| Delivery | Experiment Code ADS Test case Architectural Design Protocol Design |  |  |  | 1. Our QA is OK? 2. is experiment included in Analysis or Implementation? 3.
| Demo | Mentor Review
ID | Backlogs |  | Comment |  | To-Do |  | In Progress |  |  | Done |  |  | Daily Report (Time Logs)
| Category | Item |  |  | Logs | Assingnee | Logs | Start date | Estimated time | Logs | End date | Used time | Sunghoon | Gunwoo | Gladvin | Wonhong | Sangjun | Beney
1 | Plan | Sprint 2 planning |  |  | Sprint 2 planning | All (except Gunwoo, Gladvin) | Sprint 2 planning | 2016-06-03 | 3 |  | 2016-06-03 | 22.6 | 4 | 3 | 3 | 4 | 4.3 | 4.3 | 22.6
2 |  | Mentor Meeting |  |  | Mentor Meeting | All |  | 2016-05-31 | 6 | Mentor Meeting | 2016-05-31 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 6
3 | Analysis | Use case scenario |  | 1 | Use case scenario | All (except Gunwoo, Gladvin) |  | 2016-05-31 | 16 | Use case scenario | 2016-06-01 | 20.5 | 5.5 |  |  | 1 | 7 | 7 | 20.5
4 |  | Context Diagram (ADS) |  |  | Context Diagram (ADS) | Wonhong |  | 2016-05-31 | 2 | Context Diagram (ADS) | 2016-06-01 | 2 |  |  |  | 2 |  |  | 2
5 |  | FR refine |  |  | FR refine | Wonhong | FR refine | 2016-05-31 | 2 |  |  | 4 | 4 | [5 empty] | 4
6 |  | QA refine |  | 2 | QA refine | All(except Gunwoo, Gladvin) |  | 2016-05-31 | 16 | QA refine | 2016-06-02 | 9 |  |  |  |  | 4.5 | 4.5 | 9
7 |  | Constraint refine |  |  | Constraint refine | Wonhong | Constraint refine | 2016-05-31 | 2 |  |  | 0 | [6 empty] | 0
8 | Design | Reserach Architetual Pattern |  | 3 | Reserach Architetual Pattern | All(except Gunwoo, Gladvin) |  | 2016-06-03 | 40 | Reserach Architetual Pattern | 2016-06-06 | 32.7 | 6 | 4.5 | 2 | 6 | 7.1 | 7.1 | 32.7
9 |  | Researchi Tactic |  | 4 | Research Tactic | All(except Gunwoo, Gladvin) | Research Tactic | 2016-06-03 |  |  |  | 2.1 | 2 |  |  |  |  | 0.1 | 2.1
10 | Experiment | Arduino MQTT Client | Based on PubSubClient Library |  | Arduino MQTT Client | Gunwoo |  | 2016-05-31 | 4 | Arduino MQTT Client | 2016-06-01 | 5 |  | 5 |  |  |  |  | 5
11 |  | Java MQTT Client (Server and Application) | Based on Paho MQTT Client Library |  | Java MQTT Client (Server and Application) | Gladvin |  | 2016-05-31 | 8 | Java MQTT Client (Server and Application) | 2016-06-01 | 6 |  |  | 6 |  |  |  | 6
12 |  | Prototypes #1: Open/Close the gate from App |  |  | Prototypes #1: Open/Close the gate from App | Gunwoo, Gladvin |  | 2016-05-31 | 4 | Prototypes #1: Open/Close the gate from App | 2016-06-01 | 3 |  | 3 |  |  |  |  | 3
13 |  | Prototypes #2: Show the slot status on App |  |  | Prototypes #2: Show the slot status on App | Gunwoo, Gladvin |  | 2016-05-31 | 4 | Prototypes #2: Show the slot status on App | 2016-06-03 | 16 |  | 6 | 10 |  |  |  | 16
14 |  | Java HTTP Server | Based on Vert.X |  | Java HTTP Server | Gladvin | Java HTTP Server |  | 3 |  |  | 0 | [6 empty] | 0
15 |  | Java MySQL Client | Based on Vert.X |  | Java MySQL Client | Gunwoo | Java MySQL Client | 2016-05-31 | 3 |  |  | 1 |  | 1 |  |  |  |  | 1
16 |  | Prototypes #3: Save the slot status into MySQL |  |  | Prototypes #3: Save the slot status into MySQL | Gunwoo, Gladvin | Prototypes #3: Save the slot status into MySQL |  | 3 |  |  | 0 | [6 empty] | 0
17 |  | Prototypes #4: REST API which returns the slot status |  |  | Prototypes #4: REST API which returns the slot status | Gunwoo, Gladvin | Prototypes #4: REST API which returns the slot status |  | 3 |  |  | 0 | [6 empty] | 0
18 |  | Secure Communication between Arduino and Server | SSL, HTTPS, MQTT ID/Pass |  | Secure Communication between Arduino and Server | Gunwoo, Gladvin | Secure Communication between Arduino and Server |  | 4 |  |  | 0 | [6 empty] | 0
19 | Implementation | PC environment setup |  |  | PC environment setup | All |  |  | 3 | PC environment setup | 2016-06-03 | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3
20 |  | Git Hub |  |  | Git Hub | Sangjun |  |  | 1 | Git Hub | 2016-05-31 | 0 | [6 empty] | 0
21 | documentation | Sprint and Time log v1.0 |  |  | Sprint and Time log v1.0 | Sunghoon | Sprint and Time log v1.0 | 2016-05-31 | 2 |  |  | 0.2 | 0.2 | [5 empty] | 0.2
22 |  | ADS |  |  | ADS | Wonhong | ADS |  | 4 |  |  | 6 |  |  |  | 6 |  |  | 6
23 |  | risk management |  |  | risk management | beney | risk management |  | 2 |  |  | 0 | [6 empty] | 0
24 |  | test plan |  |  | test plan | Sangjun | test plan |  | 6 |  |  | 0 | [6 empty] | 0
[13 empty] | 23.2 | 24 | 22.5 | 20.5 | 24.4 | 24.5

## Sprint2
| Sprint Period | 6/5 ~ 6/11
| Story | implement basic scenarios (reservation, parking without considering security) |  |  | Question
| Delivery | documents(Detail Design- 2nd Decomposition, tracking, UI, Test case, Risk), SW (Facility, App, Server)
Demo
ID | Backlogs |  |  | To-Do |  | In Progress |  |  | Done |  |  | Daily Report (Time Logs)
| Category | item |  | Logs | Assingnee | Logs | start date | Estimated time | Logs | End date | Used time | Sunghoon | Gunwoo | Gladvin | wonhong | sangjun | beney
1 | Plan | Sprint 3 planning |  | Sprint 3 planning | All | Sprint 3 planning | 2016-06-10 | 1 | Sprint 3 planning | 2016-06-10 | 1 | 0.5 | 0.5 |  |  |  |  | 1
2 |  | Mentor Meeting |  | Mentor Meeting | All | Mentor Meeting | 2016-06-06 | 6 | Mentor Meeting | 2016-06-06 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 6
3 |  | Risk Mitigation Meeting |  | Risk Mitigation Meeting | Beney Kim | Risk Mitigation Meeting |  | 1 | Risk Mitigation Meeting |  | 0 | [6 empty] | 0
4 | Analysis | FR refine |  | FR refine | Wonhong Kwon | FR refine |  | 2 |  |  | 1 |  |  |  | 1 |  |  | 1
5 |  | QA refine |  | QA refine | Wonhong Kwon | QA refine |  | 4 |  |  | 2 |  |  |  | 2 |  |  | 2
6 |  | Constraint refine |  | Constraint refine | Wonhong Kwon | [5 empty] | 0 | [6 empty] | 0
7 |  | Use case refine |  | Use case refine | All | [5 empty] | 0 | [6 empty] | 0
8 | Experiment | MQTT Security - SSL |  | MQTT Security - SSL | Gladvin | MQTT Security - SSL | 2016-06-08 | 4 |  |  | 5 |  |  | 5 |  |  |  | 5
9 |  | MQTT Security - ID / PASS |  | MQTT Security - ID / PASS | Gladvin | MQTT Security - ID / PASS | 2016-06-08 | 4 |  |  | 0 | [6 empty] | 0
10 |  | Arduino to Java Application via USB |  | Arduino to Java Application via USB | Sangjun | Arduino to Java Application via USB | 2016-06-08 | 4 | Arduino to Java Application via USB |  | 0 | [6 empty] | 0
11 |  | Vert.X Server to MySQL |  | Vert.X Server to MySQL |  | Vert.X Server to MySQL | 2016-06-08 | 2 | Vert.X Server to MySQL | 2016-06-08 | 2 |  | 2 |  |  |  |  | 2
12 | Design | Reserach Architetual Pattern |  | Reserach Architetual Pattern | All | Reserach Architetual Pattern | 2016-06-06 | 10 |  |  | 16.5 | 4.5 |  | 2 | 6 |  | 4 | 16.5
13 |  | Research Tactic |  | Research Tactic | All | Research Tactic | 2016-06-06 | 10 |  |  | 3 | 3 | [5 empty] | 3
14 |  | Start Static View design |  | Start Static View design | All | Start Static View design | 2016-06-08 | 10 |  |  | 5 |  |  | 2 | 2 |  | 1 | 5
15 |  | Start Dynamic View design |  | Start Dynamic View design | All | Start Dynamic View design | 2016-06-08 | 10 |  |  | 13 |  |  | 3 | 4 |  | 6 | 13
16 |  | Start Allocation View design |  | Start Allocation View design | All | Start Allocation View design | 2016-06-08 | 5 |  |  | 0 | [6 empty] | 0
17 |  | MQTT Topic (Protocol) |  | MQTT Topic (Protocol) | Beney, Gunwoo | MQTT Topic (Protocol) | 2016-06-08 | 10 |  |  | 13 |  | 4 | 4 |  |  | 5 | 13
18 |  | Database Schema |  | Database Schema | Gunwoo | Database Schema | 2016-06-08 | 4 | Database Schema |  | 4 |  | 4 |  |  |  |  | 4
19 | Detail Design | Make Reservation Scenario |  | Make Reservation Scenario | Beney, Gladvin, Sangun, Gunwoo | Make Reservation Scenario | 2016-06-07 |  |  |  | 0 | [6 empty] | 0
20 |  | Confirm Reservation Scenario |  | Confirm Reservation Scenario | Beney, Gladvin, Sangun, Gunwoo | Confirm Reservation Scenario | 2016-06-07 |  |  |  | 0 | [6 empty] | 0
21 |  | Parking Scenario |  | Parking Scenario | Beney, Gladvin, Sangun, Gunwoo | Parking Scenario | 2016-06-07 |  |  |  | 0 | [6 empty] | 0
22 |  | Leave Scenario |  | Leave Scenario | Beney, Gladvin, Sangun, Gunwoo | Leave Scenario | 2016-06-07 |  |  |  | 0 | [6 empty] | 0
23 | Implementation | Arbiter (MQTT porting) |  | Arbiter (MQTT porting) | Gunwoo | Arbiter (MQTT porting) | 2016-06-02 |  | Arbiter (MQTT porting) | 2016-06-03 | 0 | [6 empty] | 0
24 |  | Arbiter (MQTT + SSL) |  | Arbiter (MQTT + SSL) | Gladvin | Arbiter (MQTT + SSL) | 2016-06-06 |  |  |  | 0 | [6 empty] | 0
25 |  | Arbiter (MQTT + ID/PASSWORD) |  | Arbiter (MQTT + ID/PASSWORD) | Gladvin | Arbiter (MQTT + ID/PASSWORD) | 2016-06-07 |  |  |  | 0 | [6 empty] | 0
26 |  | Server (Network communication API) |  | Server (Network communication API) | Gunwoo | Server (Network communication API) | 2016-06-08 | 4 | Server (Network communication API) | 2016-06-12 | 13 |  | 5 |  |  |  | 8 | 13
27 |  | Server (switching function - Redundancy) |  | Server (switching function - Redundancy) | Beney | Server (switching function - Redundancy) | 2016-06-09 |  | Server (switching function - Redundancy) | 2016-06-10 | 0 | [6 empty] | 0
28 |  | Server (RDB Construction) |  | Server (RDB Construction) | Gunwoo | Server (RDB Construction) | 2016-06-06 | 2 | Server (RDB Construction) | 2016-06-10 | 2 |  | 2 |  |  |  |  | 2
29 |  | Server (RDB Proxy) |  | Server (RDB Proxy) | Gunwoo | Server (RDB Proxy) | 2016-06-07 | 4 | Server (RDB Proxy) | 2016-06-11 | 3 |  | 3 |  |  |  |  | 3
30 |  | Server (reservation logic) |  | Server (reservation logic) | Gunwoo | [5 empty] | 0 | [6 empty] | 0
31 |  | Server (sign up) |  | Server (sign up) | Gunwoo | [5 empty] | 0 | [6 empty] | 0
32 |  | Server (log in/out) |  | Server (log in/out) | Gunwoo | [5 empty] | 0 | [6 empty] | 0
33 |  | Server (status check logic) |  | Server (status check logic) | Gunwoo | [5 empty] | 0 | [6 empty] | 0
34 |  | Server (statistics logic - data collection) |  | Server (statistics logic - data collection) | Gunwoo | [5 empty] | 0 | [6 empty] | 0
35 |  | Server (facility control logic) |  | Server (facility control logic) | Gunwoo | [5 empty] | 0 | [6 empty] | 0
36 |  | Server (push service - alarm) |  | Server (push service - alarm) | Gunwoo | [5 empty] | 0 | [6 empty] | 0
37 |  | Facility(Network communication API) |  | Facility(Network communication API) | Gladvin, Sangun | [5 empty] | 4 |  |  |  |  | 4 |  | 4
38 |  | Facility(Kiosk communication API) |  | Facility(Kiosk communication API) | Gladvin, Sangun | [5 empty] | 4 |  |  |  |  | 4 |  | 4
39 |  | Facility(Sensor logic) |  | Facility(Sensor logic) | Gladvin, Sangun | [5 empty] | 4 |  |  |  |  | 4 |  | 4
40 |  | Facility(Adding new facility slot logic) |  | Facility(Adding new facility slot logic) | Gladvin, Sangun | [5 empty] | 0 | [6 empty] | 0
41 |  | Facility(reservation checking) |  | Facility(reservation checking) | Gladvin, Sangun | [5 empty] | 0 | [6 empty] | 0
42 |  | Kiosk(UI) |  | Kiosk(UI) | Gladvin, Sangun | [5 empty] | 0 | [6 empty] | 0
43 |  | Kiosk(USB communication API) |  | Kiosk(USB communication API) | Gladvin, Sangun | [5 empty] | 0 | [6 empty] | 0
44 |  | Kiosk(Facility communication API) |  | Kiosk(Facility communication API) | Gladvin, Sangun | [5 empty] | 0 | [6 empty] | 0
45 |  | Driver Application (Network communication API) |  | Driver Application (Network communication API) | Beney | Driver Application (Network communication API) | 2016-06-08 |  |  |  | 8 | [5 empty] | 8 | 8
46 |  | Driver Application (UI) |  | Driver Application (UI) | Beney | [5 empty] | 0 | [6 empty] | 0
47 |  | Driver Application (sign in) |  | Driver Application (sign in) | Beney | [5 empty] | 0 | [6 empty] | 0
48 |  | Driver Application (log in/out) |  | Driver Application (log in/out) | Beney | [5 empty] | 0 | [6 empty] | 0
49 |  | Driver Application (reservation logic) |  | Driver Application (reservation logic) | Beney | [5 empty] | 0 | [6 empty] | 0
50 |  | Driver Application (Popup message) |  | Driver Application (Popup message) | Beney | [5 empty] | 0 | [6 empty] | 0
51 |  | Owner Application(Network communication API) |  | Owner Application(Network communication API) | Gladvin | Owner Application(Network communication API) | 2016-06-08 |  |  |  | 4 | [5 empty] | 4 | 4
52 |  | Owner Application(UI) |  | Owner Application(UI) | Gladvin | [5 empty] | 0 | [6 empty] | 0
53 |  | Owner Application(log in/out) |  | Owner Application(log in/out) | Gladvin | [5 empty] | 0 | [6 empty] | 0
54 |  | Owner Application(statistics logic) |  | Owner Application(statistics logic) | Gladvin | [5 empty] | 0 | [6 empty] | 0
55 |  | Owner Application(configuration logic) |  | Owner Application(configuration logic) | Gladvin | [5 empty] | 0 | [6 empty] | 0
56 |  | Owner Application(Popup message) |  | Owner Application(Popup message) | Gladvin | [5 empty] | 0 | [6 empty] | 0
57 |  | Attendant Application(Network communication API) |  |  |  | Attendant Application(Network communication API) | 2016-06-08 |  |  |  | 0 | [6 empty] | 0
58 |  | Attendant Application(UI) | [8 empty] | 0 | [6 empty] | 0
59 |  | Attendant Application(log in/out) | [8 empty] | 0 | [6 empty] | 0
60 |  | Attendant Application(status check logic) | [8 empty] | 0 | [6 empty] | 0
61 |  | Attendant Application(Popup message) | [8 empty] | 0 | [6 empty] | 0
62 | Testing | Functional test |  | Functional test | Gladvin | [5 empty] | 4 |  |  | 4 |  |  |  | 4
63 |  | Sprint2 result test |  | Sprint2 result test | Sunghoon Yun | Sprint2 result test | 2016-06-10 | 2 | Sprint2 result test | 2016-06-10 | 2 | 2 | [5 empty] | 2
64 | Documentation | Use Case Document v1.0 |  | Use Case Document v1.0 | Wonhong Kwon | [5 empty] | 0 | [6 empty] | 0
65 |  | Architecture Driver Specification v1.0 |  | Architecture Driver Specification v1.0 | Wonhong Kwon | Architecture Driver Specification v1.0 |  | 2 |  |  | 1.5 |  |  |  | 1.5 |  |  | 1.5
66 |  | Architecture Design Document v0.1 |  | Architecture Design Document v0.1 | Wonhong Kwon | Architecture Design Document v0.1 |  | 10 |  |  | 3 |  |  | 1 | 2 |  |  | 3
67 |  | Detail Design Document v0.1 |  | Detail Design Document v0.1 | [6 empty] | 0 | [6 empty] | 0
68 |  | System test case v1.0 | [8 empty] | 0 | [6 empty] | 0
69 |  | Planning Document v1.0 |  | Planning Document v1.0 | Sunghoon Yun | Planning Document v1.0 | 2016-06-06 | 4 | Planning Document v1.0 | 2016-06-12 | 1 | 1 | [5 empty] | 1
70 |  | Sprint and Time log v1.0 |  | Sprint and Time log v1.0 | Sunghoon Yun | Sprint and Time log v1.0 | 2016-06-06 | 4 | Sprint and Time log v1.0 | 2016-06-07 | 5.5 | 5.5 | [5 empty] | 5.5
71 |  | Failure model list v1.0 |  | Failure model list v1.0 | Sunghoon Yun | Failure model list v1.0 | 2016-06-06 | 4 | Failure model list v1.0 | 2016-06-08 | 8 | 8 | [5 empty] | 8
[12 empty] | 25.5 | 21.5 | 22 | 19.5 | 13 | 37
구현 이전에 해야 할 Item
|  |  | 1 | 1st Decomposition의 3가지 view
|  |  | 2 | 2nd Decomposition의 각 view들
|  |  | 3 | rationale 이 decomposition한 곳에서 각각 잘 나와야
|  |  | 4 | MQTT Topics (Protocol)

## Sprint3
| Sprint Period | 6/12 ~ 6/18
| Story | implement basic scenarios (reservation, parking without considering security) |  |  | Question
| Delivery | documents(Detail Design- 2nd Decomposition, tracking, UI, Test case, Risk), SW (Facility, App, Server)
Demo
ID | Backlogs |  |  | To-Do |  | In Progress |  |  | Done |  |  | Daily Report (Time Logs)
| Category | item |  | Logs | Assingnee | Logs | start date | Estimated time | Logs | End date | Used time | Sunghoon | Gunwoo | Gladvin | wonhong | sangjun | beney
1 | Plan | Sprint 4 planning |  | Sprint 3 planning | All | Sprint 4 planning | 2016-06-17 | 2 | Sprint 4 planning | 2016-06-17 | 5 | 3 |  |  |  |  | 2 | 5
2 |  | Mentor Meeting |  | Mentor Meeting | All | Mentor Meeting | 2016-06-17 | 6 | Mentor Meeting | 2016-06-17 | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 12
3 |  | Risk Mitigation Meeting |  | Risk Mitigation Meeting | Beney Kim | [5 empty] | 1 | [5 empty] | 1 | 1
4 | Analysis | FR refine |  | FR refine | Wonhong Kwon | [5 empty] | 0 | [6 empty] | 0
5 |  | QA refine |  | QA refine | Wonhong Kwon | [5 empty] | 0 | [6 empty] | 0
6 |  | Constraint refine |  | Constraint refine | Wonhong Kwon | [5 empty] | 0 | [6 empty] | 0
7 |  | Use case refine |  | Use case refine | All | [5 empty] | 0 | [6 empty] | 0
8 | Experiment | MQTT Security - SSL |  | MQTT Security - SSL | Gladvin | MQTT Security - SSL | 2016-06-08 | 4 | MQTT Security - SSL |  | 6 |  |  | 6 |  |  |  | 6
9 |  | MQTT Security - ID / PASS |  | MQTT Security - ID / PASS | Gladvin | MQTT Security - ID / PASS | 2016-06-08 | 4 | MQTT Security - ID / PASS |  | 4 |  |  | 4 |  |  |  | 4
10 | Design | Reserach Architetual Pattern |  | Reserach Architetual Pattern | All | Reserach Architetual Pattern | 16.06.13 |  |  |  | 7 |  |  | 2 | 5 |  |  | 7
11 |  | Research Tactic |  | Research Tactic | All | Research Tactic | 16.06.13 |  |  |  | 6 | 1 |  |  | 5 |  |  | 6
12 |  | Start Static View design |  | Start Static View design | All | [5 empty] | 1 | 1 | [5 empty] | 1
13 |  | Start Dynamic View design |  | Start Dynamic View design | All | [5 empty] | 1 | 1 | [5 empty] | 1
14 |  | Start Allocation View design |  | Start Allocation View design | All | [5 empty] | 0 | [6 empty] | 0
15 |  | MQTT Topic (Protocol) |  | MQTT Topic (Protocol) | Beney | MQTT Topic (Protocol) | 16.06.13 | 5 |  |  | 7 |  |  | 1 |  |  | 6 | 7
16 | Detail Design | Make Reservation Scenario |  | Make Reservation Scenario | Beney, Gladvin, Sangun, Gunwoo | Make Reservation Scenario | 16.06.13 | 4 |  |  | 5 |  |  |  |  | 1 | 4 | 5
17 |  | Confirm Reservation Scenario |  | Confirm Reservation Scenario | Beney, Gladvin, Sangun, Gunwoo | [5 empty] | 1 |  |  |  |  | 1 |  | 1
18 |  | Parking Scenario |  | Parking Scenario | Beney, Gladvin, Sangun, Gunwoo | [5 empty] | 1 |  |  |  |  | 1 |  | 1
19 |  | Leave Scenario |  | Leave Scenario | Beney, Gladvin, Sangun, Gunwoo | [5 empty] | 1 |  |  |  |  | 1 |  | 1
20 |  | Arbiter (MQTT + SSL) |  | Arbiter (MQTT + SSL) | Gunwoo | [5 empty] | 0 | [6 empty] | 0
21 |  | Arbiter (MQTT + ID/PASSWORD) |  | Arbiter (MQTT + ID/PASSWORD) | Gunwoo | [5 empty] | 0 | [6 empty] | 0
22 |  | Server (Network communication API) |  | Server (Network communication API) | Gunwoo | [5 empty] | 1 | [5 empty] | 1 | 1
23 |  | Server (reservation logic) |  | Server (reservation logic) | Gunwoo | Server (reservation logic) | 16.06.13 | 8 | Server (reservation logic) | 16.06.14 | 10 |  | 10 |  |  |  |  | 10
24 |  | Server (sign up) |  | Server (sign in) | Gunwoo | Server (sign up) | 16.06.16 | 2 | Server (sign up) | 16.06.16 | 2 |  | 2 |  |  |  |  | 2
25 |  | Server (log in/out) |  | Server (log in/out) | Gunwoo | Server (log in/out) | 16.06.13 | 3 | Server (log in/out) | 16.06.15 | 3 |  | 3 |  |  |  |  | 3
26 |  | Server (status check logic) |  | Server (status check logic) | Gunwoo | Server (status check logic) | 16.06.14 | 2 | Server (status check logic) | 16.06.19 | 6 |  | 6 |  |  |  |  | 6
27 |  | Server (statistics logic - data collection) |  | Server (statistics logic - data collection) | Gunwoo | Server (statistics logic - data collection) | 16.06.17 | 2 | Server (statistics logic - data collection) | 16.06.16 | 3 |  | 3 |  |  |  |  | 3
28 |  | Server (facility control logic) |  | Server (facility control logic) | Gunwoo | Server (facility control logic) | 16.06.14 | 2 | Server (facility control logic) | 16.06.19 | 3 |  | 3 |  |  |  |  | 3
29 |  | Server (push service - alarm) |  | Server (push service - alarm) | Gunwoo | Server (push service - alarm) | 16.06.17 | 2 | Server (push service - alarm) | 16.06.19 | 3 |  | 3 |  |  |  |  | 3
30 |  | Facility(Network communication API) |  | Facility(Network communication API) | Gladvin, Sangun | Facility(Network communication API) | 16.06.14 | 4 | Facility(Network communication API) | 16.06.14 | 5 |  |  |  |  | 5 |  | 5
31 |  | Facility(Kiosk communication API) |  | Facility(Kiosk communication API) | Gladvin, Sangun | Facility(Kiosk communication API) | 16.06.15 | 4 | Facility(Kiosk communication API) | 16.06.15 | 5 |  |  |  |  | 5 |  | 5
32 |  | Facility(Sensor logic) |  | Facility(Sensor logic) | Gladvin, Sangun | Facility(Sensor logic) | 16.06.16 | 4 | Facility(Sensor logic) | 16.06.16 | 6 |  |  |  |  | 6 |  | 6
33 |  | Facility(Adding new facility slot logic) |  | Facility(Adding new facility slot logic) | Gladvin, Sangun | Facility(Adding new facility slot logic) | 16.06.17 | 4 | Facility(Adding new facility slot logic) | 16.06.17 | 4 |  |  |  |  | 4 |  | 4
34 |  | Facility(reservation checking) |  | Facility(reservation checking) | Gladvin, Sangun | Facility(reservation checking) | 16.06.18 | 4 | Facility(reservation checking) | 16.06.18 | 4 |  |  |  |  | 4 |  | 4
35 |  | Kiosk(UI) |  | Kiosk(UI) | Gladvin, Sangun | Kiosk(UI) | 16.06.13 | 4 | Kiosk(UI) | 16.06.13 | 3 |  |  |  |  | 3 |  | 3
36 |  | Kiosk(USB communication API) |  | Kiosk(USB communication API) | Gladvin, Sangun | Kiosk(USB communication API) | 16.06.13 | 3 | Kiosk(USB communication API) | 16.06.13 | 3 |  |  |  |  | 3 |  | 3
37 |  | Kiosk(Facility communication API) |  | Kiosk(Facility communication API) | Gladvin, Sangun | Kiosk(Facility communication API) | 16.06.13 | 3 | Kiosk(Facility communication API) | 16.06.13 | 3 |  |  |  |  | 3 |  | 3
38 |  | Driver Application (Network communication API) |  | Driver Application (Network communication API) | Beney | Driver Application (Network communication API) | 16.06.13 | 8 |  | 16.06.13 | 4 | [5 empty] | 4 | 4
39 |  | Driver Application (UI) |  | Driver Application (UI) | Beney |  | 16.06.13 | 8 | Driver Application (UI) | 2016-06-16 | 5 | [5 empty] | 5 | 5
40 |  | Driver Application (sign in) |  | Driver Application (sign in) | Beney |  | 16.06.13 | 4 | Driver Application (sign in) | 2016-06-16 | 2 | [5 empty] | 2 | 2
41 |  | Driver Application (log in/out) |  | Driver Application (log in/out) | Beney |  | 16.06.13 | 4 | Driver Application (log in/out) | 2016-06-16 | 2 | [5 empty] | 2 | 2
42 |  | Driver Application (reservation logic) |  | Driver Application (reservation logic) | Beney |  | 16.06.13 | 8 | Driver Application (reservation logic) | 2016-06-16 | 4 | [5 empty] | 4 | 4
43 |  | Driver Application (Popup message) |  | Driver Application (Popup message) | Beney | Driver Application (Popup message) | 2016-06-16 |  |  |  | 0 | [6 empty] | 0
44 |  | Owner Application(Network communication API) |  | Owner Application(Network communication API) | Gladvin |  | 2016-06-16 | 8 |  |  | 2 |  |  | 2 |  |  |  | 2
45 |  | Owner Application(UI) |  | Owner Application(UI) | Gladvin |  | 2016-06-14 | 15 |  |  | 8 |  |  | 8 |  |  |  | 8
46 |  | Owner Application(log in/out) |  | Owner Application(log in/out) | Gladvin |  | 2016-06-16 | 5 |  |  | 2 |  |  | 2 |  |  |  | 2
47 |  | Owner Application(statistics logic) |  | Owner Application(statistics logic) | Gladvin |  | 2016-06-14 | 30 |  |  | 8 |  |  | 8 |  |  |  | 8
48 |  | Owner Application(configuration logic) |  | Owner Application(configuration logic) | Gladvin |  | 2016-06-20 | 5 |  |  | 0 | [6 empty] | 0
49 |  | Owner Application(Popup message) |  | Owner Application(Popup message) | Gladvin |  | 2016-06-20 | 5 |  |  | 0 | [6 empty] | 0
50 |  | Attendant Application(Network communication API) |  | Attendant Application(Network communication API) | Beney | Attendant Application(Network communication API) | 2016-06-16 | 2 |  |  | 2 | [5 empty] | 2 | 2
51 |  | Attendant Application(UI) |  | Attendant Application(UI) | Beney |  | 2016-06-16 | 2 | Attendant Application(UI) | 2016-06-16 | 2 | [5 empty] | 2 | 2
52 |  | Attendant Application(log in/out) |  | Attendant Application(log in/out) | Beney |  | 2016-06-16 | 1 | Attendant Application(log in/out) | 2016-06-16 | 2 | [5 empty] | 2 | 2
53 |  | Attendant Application(status check logic) |  | Attendant Application(status check logic) | Beney | Attendant Application(status check logic) | 2016-06-16 | 4 |  |  | 2 | [5 empty] | 2 | 2
54 |  | Attendant Application(Popup message) |  | Attendant Application(Popup message) | Beney | Attendant Application(Popup message) | 2016-06-16 | 2 |  |  | 0 | [6 empty] | 0
56 | Testing | System test |  | System test | Sunghoon Yun | System test | 2016-06-16 | 2 | System test | 2016-06-16 | 4 | 4 | [5 empty] | 4
57 | Documentation | Use Case Document v1.0 |  | Use Case Document v1.0 | Wonhong Kwon | [5 empty] | 0 | [6 empty] | 0
58 |  | Architecture Driver Specification v1.0 |  | Architecture Driver Specification v1.0 | Wonhong Kwon | [5 empty] | 0 | [6 empty] | 0
59 |  | Architecture Design Document v0.1 |  | Architecture Design Document v1.0 | Wonhong Kwon | Architecture Design Document v1.0 | 16.06.13 |  |  |  | 11 | 2 |  |  | 9 |  |  | 11
60 |  | Detail Design Document v0.1 |  | Detail Design Document v0.1 | [6 empty] | 0 | [6 empty] | 0
61 |  | System test case v1.0 |  | System test case v1.0 | Sunghoon Yun | System test case v1.0 | 2016-06-14 | 8 | System test case v1.0 | 2016-06-16 | 10 | 10 | [5 empty] | 10
[12 empty] | 24 | 32 | 35 | 21 | 39 | 41
구현 이전에 해야 할 Item
|  |  | 1 | 1st Decomposition의 3가지 view
|  |  | 2 | 2nd Decomposition의 각 view들
|  |  | 3 | rationale 이 decomposition한 곳에서 각각 잘 나와야
|  |  | 4 | MQTT Topics (Protocol)

## Sprint4
| Sprint Period | 6/20 ~ 6/23
| Story | Test and debugging
| Delivery | documents(final presentation), SW (All function)
Demo
ID | Backlogs |  | To-Do |  | In Progress |  |  | Done |  |  | Daily Report (Time Logs)
| Category | item | Logs | Assingnee | Logs | start date | Estimated time | Logs | End date | Used time | Sunghoon | Gunwoo | Gladvin | wonhong | sangjun | beney
2 |  | Mentor Meeting | Mentor Meeting | All | Mentor Meeting | 2016-06-20 | 6 | Mentor Meeting | 2016-06-20 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 6
3 |  | Risk Mitigation Meeting | Risk Mitigation Meeting | Beney Kim | [5 empty] | 0 | [6 empty] | 0
4 | Analysis | FR refine | FR refine | Wonhong Kwon | [5 empty] | 0 | [6 empty] | 0
5 |  | QA refine | QA refine | Wonhong Kwon | [5 empty] | 0 | [6 empty] | 0
6 |  | Constraint refine | Constraint refine | Wonhong Kwon | [5 empty] | 0 | [6 empty] | 0
7 |  | Use case refine | Use case refine | All | [5 empty] | 0 | [6 empty] | 0
8 | Design | Reserach Architetual Pattern | Reserach Architetual Pattern | All | Reserach Architetual Pattern | 16.06.13 |  |  |  | 4 |  |  |  | 4 |  |  | 4
9 |  | Research Tactic | Research Tactic | All | Research Tactic | 16.06.13 |  |  |  | 0 | [6 empty] | 0
10 |  | Start Static View design | Start Static View design | All | [5 empty] | 0 | [6 empty] | 0
11 |  | Start Dynamic View design | Start Dynamic View design | All | [5 empty] | 0 | [6 empty] | 0
12 |  | Start Allocation View design | Start Allocation View design | All | [5 empty] | 0 | [6 empty] | 0
13 |  | MQTT Topic (Protocol) | MQTT Topic (Protocol) | Beney |  | 16.06.13 | 5 | MQTT Topic (Protocol) | 16.06.23 | 4 | [5 empty] | 4 | 4
14 | Detail Design | Make Reservation Scenario | Make Reservation Scenario | Beney, Gladvin, Sangun, Gunwoo | Make Reservation Scenario | 16.06.13 | 4 |  |  | 0 | [6 empty] | 0
15 |  | Confirm Reservation Scenario | Confirm Reservation Scenario | Beney, Gladvin, Sangun, Gunwoo | Confirm Reservation Scenario | 16.06.13 |  |  |  | 0 | [6 empty] | 0
16 |  | Parking Scenario | Parking Scenario | Beney, Gladvin, Sangun, Gunwoo | Parking Scenario | 16.06.13 |  |  |  | 0 | [6 empty] | 0
17 |  | Leave Scenario | Leave Scenario | Beney, Gladvin, Sangun, Gunwoo | Leave Scenario | 16.06.13 |  |  |  | 0 | [6 empty] | 0
18 |  | Arbiter (MQTT + SSL) | Arbiter (MQTT + SSL) | Gladvin | [5 empty] | 0 | [6 empty] | 0
19 |  | Arbiter (MQTT + ID/PASSWORD) | Arbiter (MQTT + ID/PASSWORD) | Gladvin | [5 empty] | 0 | [6 empty] | 0
20 |  | Server(Checkpoint) | Server(Checkpoint) | Gunwoo | Server(Checkpoint) | 16.06.21 | 6 | Server(Checkpoint) | 16.06.21 | 3 |  | 3 |  |  |  |  | 3
21 |  | Server(Parking Transaction) | Server(Parking Transaction) | Gunwoo | Server(Parking Transaction) | 16.06.20 | 6 | Server(Parking Transaction) | 16.06.21 | 5 |  | 5 |  |  |  |  | 5
22 |  | Server(Slot Reallocation) | Server(Slot Reallocation) | Gunwoo | Server(Slot Reallocation) | 16.06.20 | 4 | Server(Slot Reallocation) | 16.06.21 | 6 |  | 6 |  |  |  |  | 6
23 |  | Server(Grace Period) | Server(Grace Period) | Gunwoo | Server(Grace Period) | 16.06.20 | 4 | Server(Grace Period) | 16.06.20 | 2 |  | 2 |  |  |  |  | 2
24 |  | Facility(Network communication API) | Facility(Network communication API) | Sangun | [5 empty] | 0 | [6 empty] | 0
25 |  | Facility(Kiosk communication API) | Facility(Kiosk communication API) | Sangun | Add comm. api | 16.06.21 | 4 |  |  | 7 |  |  |  |  | 7 |  | 7
26 |  | Facility(Sensor logic) | Facility(Sensor logic) | Sangun | [5 empty] | 0 | [6 empty] | 0
27 |  | Facility(Adding new facility slot logic) | Facility(Adding new facility slot logic) | Sangun | [5 empty] | 0 | [6 empty] | 0
28 |  | Facility(reservation checking) | Facility(reservation checking) | Sangun | Facility) handling exceptions | 16.06.20 | 8 |  |  | 10 |  |  |  |  | 10 |  | 10
29 |  | Kiosk(UI) | Kiosk(UI) | Sangun | add popup(error, noti) | 16.06.22 | 8 |  |  | 8 |  |  |  |  | 8 |  | 8
30 |  | Kiosk(USB communication API) | Kiosk(USB communication API) | Sangun | Add comm. api | 16.06.21 | 4 |  |  | 4 |  |  |  |  | 4 |  | 4
31 |  | Kiosk(Facility communication API) | Kiosk(Facility communication API) | Sangun | [5 empty] | 0 | [6 empty] | 0
32 |  | Driver Application (Network communication API) | Driver Application (Network communication API) | Beney |  | 16.06.13 | 8 | Driver Application (Network communication API) | 16.06.23 | 0 | [6 empty] | 0
33 |  | Driver Application (Popup message) | Driver Application (Popup message) | Beney |  | 2016-06-16 |  | Driver Application (Popup message) | 16.06.23 | 2 | [5 empty] | 2 | 2
34 |  | Owner Application(Network communication API) | Owner Application(Network communication API) | Gladvin | [5 empty] | 1 |  |  | 1 |  |  |  | 1
35 |  | Owner Application(UI) | Owner Application(UI) | Gladvin | [5 empty] | 4 |  |  | 4 |  |  |  | 4
36 |  | Owner Application(log in/out) | Owner Application(log in/out) | Gladvin |  |  |  | Owner Application(log in/out) | 2016-06-19 | 1 |  |  | 1 |  |  |  | 1
37 |  | Owner Application(statistics logic) | Owner Application(statistics logic) | Gladvin | [5 empty] | 2 |  |  | 2 |  |  |  | 2
38 |  | Owner Application(configuration logic) | Owner Application(configuration logic) | Gladvin | [5 empty] | 0 | [6 empty] | 0
39 |  | Owner Application(Popup message) | Owner Application(Popup message) | Gladvin | [5 empty] | 0 | [6 empty] | 0
40 |  | Attendant Application(Network communication API) | Attendant Application(Network communication API) | Beney |  | 2016-06-16 | 2 | Attendant Application(Network communication API) | 2016-06-19 | 1 | [5 empty] | 1 | 1
41 |  | Attendant Application(status check logic) | Attendant Application(status check logic) | Beney |  | 2016-06-16 | 4 | Attendant Application(status check logic) | 2016-06-19 | 3 | [5 empty] | 3 | 3
42 |  | Attendant Application(Popup message) | Attendant Application(Popup message) | Beney |  | 2016-06-16 | 2 | Attendant Application(Popup message) | 2016-06-19 | 2 | [5 empty] | 2 | 2
43 | Testing | System test | System test | Sunghoon | System test | 2016-06-20 | 4 | System test | 2016-06-21 | 9 | 6 |  |  |  |  | 3 | 9
45 | Documentation | Use Case Document v1.0 | Use Case Document v1.0 | Wonhong Kwon | [5 empty] | 0 | [6 empty] | 0
46 |  | Architecture Driver Specification v1.0 | Architecture Driver Specification v1.0 | Wonhong Kwon | [5 empty] | 1 |  |  |  | 1 |  |  | 1
47 |  | Architecture Design Document v0.1 | Architecture Design Document v1.0 | Wonhong Kwon | Architecture Design Document v1.0 | 16.06.13 |  |  |  | 25 |  |  |  | 25 |  |  | 25
48 |  | Detail Design Document v0.1 | Detail Design Document v0.1 | Beney, Gladvin, Sangun, Gunwoo | Detail Design Document v0.1 | 16.06.20 | 20 |  |  | 9 |  | 6 |  |  |  | 3 | 9
49 |  | Protocol Design Document | Protocol Design Document | Beney |  | 16.06.13 |  | Protocol Design Document | 16.06.22 | 0 | [6 empty] | 0
50 |  | Final presentation & demo | Final presentation | Wonhong, Sunghoon | Final presentation | 16.06.22 |  |  |  | 18 | 12 |  |  |  |  | 6 | 18
51 |  | System test case v1.1 | System test case v1.1 | Sunghoon | System test case v1.1 | 2016-06-20 | 8 | System test case v1.1 | 2016-06-21 | 4 | 4 | [5 empty] | 4
[11 empty] | 23 | 23 | 9 | 31 | 30 | 25

## summary
[6 empty] | Sprint Period | 6/5 ~ 6/11 |  |  |  |  | Sprint Period | 6/12 ~ 6/18 |  |  |  |  | Sprint Period | 6/20 ~ 6/23
Sprint Period | 5/22 ~ 6/4 |  |  |  |  | Story | implement basic scenarios (reservation, parking without considering security) |  |  |  |  | Story | implement basic scenarios (reservation, parking without considering security) |  |  |  |  | Story | Test and debugging
Story | Make Design Document and prepare Implementation |  |  |  |  | Delivery | documents(Detail Design- 2nd Decomposition, tracking, UI, Test case, Risk), SW (Facility, App, Server) |  |  |  |  | Delivery | documents(Detail Design- 2nd Decomposition, tracking, UI, Test case, Risk), SW (Facility, App, Server) |  |  |  |  | Delivery | documents(final presentation), SW (All function)
Delivery | Experiment Code ADS Test case Architectural Design Protocol Design |  |  |  |  | Demo | [5 empty] | Demo | [5 empty] | Demo
Demo | Mentor Review
[6 empty] | Backlogs | [5 empty] | Backlogs | [5 empty] | Backlogs
[6 empty] | Category | item | Estimated time |  | Used time |  | Category | item | Estimated time |  | Used time |  | Category | item | Estimated time |  | Used time
[6 empty] | Plan | Sprint 3 planning | 1 | 8 | 1 | 7 | Plan | Sprint 4 planning | 2 | 8 | 5 | 18 |  | Mentor Meeting | 6 | 6 | 6 | 6
Backlogs | [6 empty] | Mentor Meeting | 6 |  | 6 |  |  | Mentor Meeting | 6 |  | 12 |  |  | Risk Mitigation Meeting |  |  | 0
Category | Item | Estimated time |  | Used time |  |  | Risk Mitigation Meeting | 1 |  | 0 |  |  | Risk Mitigation Meeting |  |  | 1 |  | Analysis | FR refine |  |  | 0 | 0
Plan | Sprint 2 planning | 3 | 9 | 22.6 | 28.6 | Analysis | FR refine | 2 | 6 | 1 | 3 | Analysis | FR refine |  | 0 | 0 | 0 |  | QA refine |  |  | 0
| Mentor Meeting | 6 |  | 6 |  |  | QA refine | 4 |  | 2 |  |  | QA refine |  |  | 0 |  |  | Constraint refine |  |  | 0
Analysis | Use case scenario | 16 | 38 | 20.5 | 35.5 |  | Constraint refine |  |  | 0 |  |  | Constraint refine |  |  | 0 |  |  | Use case refine |  |  | 0
| Context Diagram (ADS) | 2 |  | 2 |  |  | Use case refine |  |  | 0 |  |  | Use case refine |  |  | 0 |  | Design | Reserach Architetual Pattern |  | 5 | 4 | 8
| FR refine | 2 |  | 4 |  | Experiment | MQTT Security - SSL | 4 | 14 | 5 | 7 | Experiment | MQTT Security - SSL |  | 0 | 6 | 10 |  | Research Tactic |  |  | 0
| QA refine | 16 |  | 9 |  |  | MQTT Security - ID / PASS | 4 |  | 0 |  |  | MQTT Security - ID / PASS |  |  | 4 |  |  | Start Static View design |  |  | 0
| Constraint refine | 2 |  | 0 |  |  | Arduino to Java Application via USB | 4 |  | 0 |  | Design | Reserach Architetual Pattern |  | 0 | 7 | 22 |  | Start Dynamic View design |  |  | 0
Design | Reserach Architetual Pattern | 40 | 40 | 32.7 | 34.8 |  | Vert.X Server to MySQL | 2 |  | 2 |  |  | Research Tactic |  |  | 6 |  |  | Start Allocation View design |  |  | 0
| Researchi Tactic |  |  | 2.1 |  | Design | Reserach Architetual Pattern | 10 | 59 | 16.5 | 54.5 |  | Start Static View design |  |  | 1 |  |  | MQTT Topic (Protocol) | 5 |  | 4
Experiment | Arduino MQTT Client | 4 | 36 | 5 | 31 |  | Research Tactic | 10 |  | 3 |  |  | Start Dynamic View design |  |  | 1 |  | Detail Design | Make Reservation Scenario | 4 | 4 | 0 | 0
| Java MQTT Client (Server and Application) | 8 |  | 6 |  |  | Start Static View design | 10 |  | 5 |  |  | Start Allocation View design |  |  | 0 |  |  | Confirm Reservation Scenario |  |  | 0
| Prototypes #1: Open/Close the gate from App | 4 |  | 3 |  |  | Start Dynamic View design | 10 |  | 13 |  |  | MQTT Topic (Protocol) |  |  | 7 |  |  | Parking Scenario |  |  | 0
| Prototypes #2: Show the slot status on App | 4 |  | 16 |  |  | Start Allocation View design | 5 |  | 0 |  | Detail Design | Make Reservation Scenario | 4 | 4 | 5 | 8 |  | Leave Scenario |  |  | 0
| Java HTTP Server | 3 |  | 0 |  |  | MQTT Topic (Protocol) | 10 |  | 13 |  |  | Confirm Reservation Scenario |  |  | 1 |  | Implementation | Arbiter (MQTT + SSL) |  | 52 | 0 | 61
| Java MySQL Client | 3 |  | 1 |  |  | Database Schema | 4 |  | 4 |  |  | Parking Scenario |  |  | 1 |  |  | Arbiter (MQTT + ID/PASSWORD) |  |  | 0
| Prototypes #3: Save the slot status into MySQL | 3 |  | 0 |  | Detail Design | Make Reservation Scenario |  | 0 | 0 | 0 |  | Leave Scenario |  |  | 1 |  |  | Server(Checkpoint) | 6 |  | 3
| Prototypes #4: REST API which returns the slot status | 3 |  | 0 |  |  | Confirm Reservation Scenario |  |  | 0 |  | Implementation | Arbiter (MQTT + SSL) |  | 162 | 0 | 109 |  | Server(Parking Transaction) | 6 |  | 5
| Secure Communication between Arduino and Server | 4 |  | 0 |  |  | Parking Scenario |  |  | 0 |  |  | Arbiter (MQTT + ID/PASSWORD) |  |  | 0 |  |  | Server(Slot Reallocation) | 4 |  | 6
Implementation | PC environment setup | 3 | 4 | 3 | 3 |  | Leave Scenario |  |  | 0 |  |  | Server (Network communication API) |  |  | 1 |  |  | Server(Grace Period) | 4 |  | 2
| Git Hub | 1 |  | 0 |  | Implementation | Arbiter (MQTT porting) |  | 10 | 0 | 42 |  | Server (reservation logic) | 8 |  | 10 |  |  | Facility(Network communication API) |  |  | 0
documentation | Sprint and Time log v1.0 | 2 | 14 | 0.2 | 6.2 |  | Arbiter (MQTT + SSL) |  |  | 0 |  |  | Server (sign up) | 2 |  | 2 |  |  | Facility(Kiosk communication API) |  |  | 7
| ADS | 4 |  | 6 |  |  | Arbiter (MQTT + ID/PASSWORD) |  |  | 0 |  |  | Server (log in/out) | 3 |  | 3 |  |  | Facility(Sensor logic) |  |  | 0
| risk management | 2 |  | 0 |  |  | Server (Network communication API) | 4 |  | 13 |  |  | Server (status check logic) | 2 |  | 6 |  |  | Facility(Adding new facility slot logic) |  |  | 0
| test plan | 6 |  | 0 |  |  | Server (switching function - Redundancy) |  |  | 0 |  |  | Server (statistics logic - data collection) | 2 |  | 3 |  |  | Facility(reservation checking) | 4 |  | 10
[7 empty] | Server (RDB Construction) | 2 |  | 2 |  |  | Server (facility control logic) | 2 |  | 3 |  |  | Kiosk(UI) | 8 |  | 8
[7 empty] | Server (RDB Proxy) | 4 |  | 3 |  |  | Server (push service - alarm) | 2 |  | 3 |  |  | Kiosk(USB communication API) | 4 |  | 4
[7 empty] | Server (reservation logic) |  |  | 0 |  |  | Facility(Network communication API) | 4 |  | 5 |  |  | Kiosk(Facility communication API) |  |  | 0
[7 empty] | Server (sign up) |  |  | 0 |  |  | Facility(Kiosk communication API) | 4 |  | 5 |  |  | Driver Application (Network communication API) | 8 |  | 0
[7 empty] | Server (log in/out) |  |  | 0 |  |  | Facility(Sensor logic) | 4 |  | 6 |  |  | Driver Application (Popup message) |  |  | 2
[7 empty] | Server (status check logic) |  |  | 0 |  |  | Facility(Adding new facility slot logic) | 4 |  | 4 |  |  | Owner Application(Network communication API) |  |  | 1
[7 empty] | Server (statistics logic - data collection) |  |  | 0 |  |  | Facility(reservation checking) | 4 |  | 4 |  |  | Owner Application(UI) |  |  | 4
[7 empty] | Server (facility control logic) |  |  | 0 |  |  | Kiosk(UI) | 4 |  | 3 |  |  | Owner Application(log in/out) |  |  | 1
[7 empty] | Server (push service - alarm) |  |  | 0 |  |  | Kiosk(USB communication API) | 3 |  | 3 |  |  | Owner Application(statistics logic) |  |  | 2
[7 empty] | Facility(Network communication API) |  |  | 4 |  |  | Kiosk(Facility communication API) | 3 |  | 3 |  |  | Owner Application(configuration logic) |  |  | 0
[7 empty] | Facility(Kiosk communication API) |  |  | 4 |  |  | Driver Application (Network communication API) | 8 |  | 4 |  |  | Owner Application(Popup message) |  |  | 0
[7 empty] | Facility(Sensor logic) |  |  | 4 |  |  | Driver Application (UI) | 8 |  | 5 |  |  | Attendant Application(Network communication API) | 2 |  | 1
[7 empty] | Facility(Adding new facility slot logic) |  |  | 0 |  |  | Driver Application (sign in) | 4 |  | 2 |  |  | Attendant Application(status check logic) | 4 |  | 3
[7 empty] | Facility(reservation checking) |  |  | 0 |  |  | Driver Application (log in/out) | 4 |  | 2 |  |  | Attendant Application(Popup message) | 2 |  | 2
[7 empty] | Kiosk(UI) |  |  | 0 |  |  | Driver Application (reservation logic) | 8 |  | 4 |  | Testing | System test | 4 | 4 | 9 | 9
[7 empty] | Kiosk(USB communication API) |  |  | 0 |  |  | Driver Application (Popup message) |  |  | 0 |  | Documentation | Use Case Document v1.0 |  | 40 | 0 | 57
[7 empty] | Kiosk(Facility communication API) |  |  | 0 |  |  | Owner Application(Network communication API) | 8 |  | 2 |  |  | Architecture Driver Specification v1.0 |  |  | 1
[7 empty] | Driver Application (Network communication API) |  |  | 8 |  |  | Owner Application(UI) | 15 |  | 8 |  |  | Architecture Design Document v0.1 |  |  | 25
[7 empty] | Driver Application (UI) |  |  | 0 |  |  | Owner Application(log in/out) | 5 |  | 2 |  |  | Detail Design Document v0.1 | 20 |  | 9
[7 empty] | Driver Application (sign in) |  |  | 0 |  |  | Owner Application(statistics logic) | 30 |  | 8 |  |  | Protocol Design Document |  |  | 0
[7 empty] | Driver Application (log in/out) |  |  | 0 |  |  | Owner Application(configuration logic) | 5 |  | 0 |  |  | Final presentation & demo | 12 |  | 18
[7 empty] | Driver Application (reservation logic) |  |  | 0 |  |  | Owner Application(Popup message) | 5 |  | 0 |  |  | System test case v1.1 | 8 |  | 4
[7 empty] | Driver Application (Popup message) |  |  | 0 |  |  | Attendant Application(Network communication API) | 2 |  | 2
[7 empty] | Owner Application(Network communication API) |  |  | 4 |  |  | Attendant Application(UI) | 2 |  | 2
[7 empty] | Owner Application(UI) |  |  | 0 |  |  | Attendant Application(log in/out) | 1 |  | 2
[7 empty] | Owner Application(log in/out) |  |  | 0 |  |  | Attendant Application(status check logic) | 4 |  | 2
[7 empty] | Owner Application(statistics logic) |  |  | 0 |  |  | Attendant Application(Popup message) | 2 |  | 0
[7 empty] | Owner Application(configuration logic) |  |  | 0 |  | Testing | Functional test | 2 | 2 | 4 | 4
[7 empty] | Owner Application(Popup message) |  |  | 0 |  |  | Sprint2 result test |  |  | 0
[7 empty] | Attendant Application(Network communication API) |  |  | 0 |  | Documentation | Use Case Document v1.0 |  | 16 | 0 | 31
[7 empty] | Attendant Application(UI) |  |  | 0 |  |  | Architecture Driver Specification v1.0 |  |  | 11
[7 empty] | Attendant Application(log in/out) |  |  | 0 |  |  | Architecture Design Document v0.1 |  |  | 0
[7 empty] | Attendant Application(status check logic) |  |  | 0 |  |  | Detail Design Document v0.1 | 8 |  | 10
[7 empty] | Attendant Application(Popup message) |  |  | 0 |  |  | System test case v1.0 | 8 |  | 10
[6 empty] | Testing | Functional test |  | 2 | 4 | 6
[7 empty] | Sprint2 result test | 2 |  | 2
[6 empty] | Documentation | Use Case Document v1.0 |  | 24 | 0 | 19
[7 empty] | Architecture Driver Specification v1.0 | 2 |  | 1.5
[7 empty] | Architecture Design Document v0.1 | 10 |  | 3
[7 empty] | Detail Design Document v0.1 |  |  | 0
[7 empty] | System test case v1.0 |  |  | 0
[7 empty] | Planning Document v1.0 | 4 |  | 1
[7 empty] | Sprint and Time log v1.0 | 4 |  | 5.5
[7 empty] | Failure model list v1.0 | 4 |  | 8

## STATISTICS
initial estimation
Plan | 56
Analysis | 120
Design | 150
Implementation | 130
Test | 120
576
sprint estimation
| sprint1 | sprint2 | sprint3 | sprint4 | total
Plan | 9 | 8 | 8 | 6 | 31 | Plan | 31
Analysis | 38 | 6 | 0 | 0 | 44 | Analysis | 44
Experiment | 36 | 14 | 0 | 0 | 50 | Design | 50
Design | 40 | 59 | 4 | 9 | 112 | Experiment | 112
Implementation | 4 | 10 | 162 | 52 | 228 | Implementation | 228
Test |  | 2 | 2 | 4 | 8 | Test | 8
documentation | 14 | 24 | 16 | 40 | 94 | documentation | 94
| 141 | 123 | 192 | 111 | 567
actual used
| sprint1 | sprint2 | sprint3 | sprint4 | total
Plan | 28.6 | 7 | 18 | 6 | 59.6 | Plan | 59.6
Analysis | 35.5 | 3 | 0 | 0 | 38.5 | Analysis | 38.5
Experiment | 31 | 7 | 10 | 0 | 48 | Design | 48
Design | 34.8 | 54.5 | 30 | 8 | 127.3 | Experiment | 127.3
Implementation | 3 | 42 | 109 | 61 | 215 | Implementation | 215
Test |  | 6 | 4 | 9 | 19 | Test | 19
documentation | 6.2 | 19 | 31 | 57 | 113.2 | documentation | 113.2
| 139.1 | 138.5 | 202 | 141 | 620.6
compare
| Initial estimation | sprint estimation | Actual time
Plan | 56 | 31 | 59.6
Analysis | 120 | 44 | 38.5
Experiment | 0 | 50 | 48
Design | 150 | 112 | 127.3
Implementation | 130 | 228 | 215
Test | 120 | 8 | 19
documentation | 0 | 94 | 113.2